{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":3},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":164,"n_cols":16,"rows_kept":164,"merged":[[0,0,0,15],[1,0,1,15],[163,0,163,15]],"flags":["formulas_cached_only"]}
["附件1"]
["湖南省建设用地土壤污染风险管控和修复名录（截至2025年12月）"]
["序号","地块编码\n","地块名称\n","所在省","所在市","详细地址","四至范围","地块面积（m2）\n","土地使用权人","进展情况/所在阶段\n","风险管控或修复目标","风险管控或修复方案编制单位\n","风险管控或修复单位\n","风险管控或修复委托人","纳入日期","备注"]
[1,4301042260002,"长沙市岳麓区观沙岭街道三汊矶原长沙铬盐厂","湖南","长沙市","原长沙铬盐厂位于长沙市岳麓区三汊矶工业区","地块西北侧为铬渣堆，西南侧为原铬盐厂家属楼（已拆除）；地块东侧紧邻滨江景观道，景观道东临湘江；地块北侧为原湘岳化工厂（已拆除）；地块南侧为长沙锌冶炼厂（已拆除）。",83333,"长沙市滨江新城建设开发有限责任公司","正在开展效果评估","满足绿地与开敞空间用地土壤环境质量要求","生态环境部环境规划院","中科鼎实环境工程有限公司、中船第九设计研究院工程有限公司、河北省安装工程有限公司联合体；湖南新九方科技有限公司、湖南岳麓山建设集团有限公司联合体","长沙市铬污染治理有限公司","2019.4.30"]
[2,4303042270004,"湖南南天化工厂西厂区地块","湖南","湘潭市","湖南省湘潭市岳塘区昭山镇","南隔岳公岭与易家湾街为邻，西滨湘江，北屏燕子岭，东至芙蓉大道",145085.84,"湘潭产业投资发展集团有限公司","正在开展效果评估","满足商业服务业用地土壤环境质量要求","湖南省环境保护科学研究院","北京建工环境修复股份有限公司","湘潭产业投资发展集团有限公司","2019.11.5","于2022年9月19日完成了效果评估，因未达到安全利用，暂不移出目录"]
[3,4303042270001,"南天化工厂（湖南南天实业股份有限公司）东厂区地块","湖南","湘潭市","湘潭市岳塘区昭山镇","属于城郊结合部，南侧2Km左右是易家湾镇；西侧为G107国道；周边部分区域湖南城际铁路。",120060,"湘潭产业投资发展集团有限公司","已完成本轮效果评估","满足居住用地、商业服务业用地、公共管理与公共服务用地土壤环境质量要求","湖南省环境保护科学研究院","中冶南方都市环保工程技术股份有限公司-湖南省和清环境科技有限公司（联合体）","湘潭产业投资发展集团有限公司","2019.11.5","于2022年5月24日完成了效果评估，因未达到安全利用，暂不移出目录"]
[4.1,4303042260011,"湘潭市竹埠港老工业区地块-易家坪片区2","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内西北部",{"v":24134.355134,"d":"24134.36"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足交通运输用地、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.2,4303042260013,"湘潭市竹埠港老工业区地块-易家坪片区4","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内东南部,东至竹埠村村委会围墙，南至荒地西至荒地，北至乡道",{"v":5047.8,"d":"5047.80"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足绿地与开敞空间用地、居住用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.3,4303042260015,"湘潭市竹埠港老工业区地块-易家坪片区6-1","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内中部",{"v":89185.87065,"d":"89185.87"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足交通运输用地、商业服务业用地、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.4,4303042260017,"湘潭市竹埠港老工业区地块-易家坪片区7","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内西部",{"v":13385.409775,"d":"13385.41"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.5,4303042260018,"湘潭市竹埠港老工业区地块-易家坪片区8","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内中北部",{"v":45006.745788,"d":"45006.75"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足交通运输用地、陆地水域、绿地与开敞空间、商业服务业用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.6,4303042260019,"湘潭市竹埠港老工业区地块-易家坪片区9","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内北部",{"v":12147.006974,"d":"12147.01"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.7,4303042260020,"湘潭市竹埠港老工业区地块-易家坪片区10","湖南","湘潭市","湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内西北部",{"v":2133.837581,"d":"2133.84"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足交通运输用地、商业服务业用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[4.8,4303042260021,"湘潭市竹埠港老工业区地块-易家坪片区11","湖南","湘潭市","岳湘潭市岳塘区荷塘街道易家坪村","竹埠港易家坪片区内北部",{"v":17489.054485,"d":"17489.05"},"湘潭竹埠港重金属污染治理投资有限公司","已开展风险评估","满足交通运输用地、居住用地土壤环境质量要求","未明确","未明确","湘潭竹埠港重金属污染治理投资有限公司","2019.10.16"]
[5,4304222260008,"原万峰化工、宝丰化工、宏翔化工三家企业遗留地块","湖南","衡阳市","衡南县三塘镇","东北侧为蒸水河，东南侧有南华大学雨母校区、湖南工商贸易专修学校，南侧有衡阳计算机学校，西侧有民房、池塘，西南主要是林地，有少量农田",171186.08,"衡阳弘湘国有投资（控股）集团有限公司","治理修复阶段","满足居住用地土壤环境质量要求","湖南钦杰环保科技有限公司","湖南凯迪工程科技有限公司","衡阳弘湘国有投资（控股）集团公司","2020.6.12","将原4304222260008、4304222260009、4304222260010三个地块，合并为4304222260008一个地块"]
[6.1,4303042260042,"湘潭市竹埠港老工业区地块-竹埠片区1-1","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内东部，东至荒地，南至村道，西至湘潭市竹埠港建筑垃圾再利用有限公司围墙，北至原谭诚环保厂区",7375.84,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.2,4303042260043,"湘潭市竹埠港老工业区地块-竹埠片区1-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内东北部",{"v":3994.997559,"d":"3995.00"},"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.3,4303042260044,"湘潭市竹埠港老工业区地块-竹埠片区1-3","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内东北部",4738.81,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.4,4303042260046,"湘潭市竹埠港老工业区地块-竹埠片区2-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内南部，东至荒地，南至村道，西至湘潭市竹埠港建筑垃圾再利用有限公司围墙，北至村道",4324.26,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.5,4303042260047,"湘潭市竹埠港老工业区地块-竹埠片区3-1","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内南部",2483.58,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.6,4303042260048,"湘潭市竹埠港老工业区地块-竹埠片区3-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内南部",6797.55,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.7,4303042260049,"湘潭市竹埠港老工业区地块-竹埠片区3-3","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内南部",47.59,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.8,4303042260052,"湘潭市竹埠港老工业区地块-竹埠片区5-1","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内中南部，东至原谭诚环保厂区，南至湘潭市竹埠港建筑垃圾再利用有限公司围墙，西至荒地，北至原谭诚环保厂区",3267.22,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.9,4303042260053,"湘潭市竹埠港老工业区地块-竹埠片区5-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内中南部，东至原谭诚环保厂区，南至湘潭市竹埠港建筑垃圾再利用有限公司围墙，西至原谭诚环保厂区，北至原谭诚环保厂区",1485.98,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[{"v":6.1,"d":"6.10"},4303042260054,"湘潭市竹埠港老工业区地块-竹埠片区6","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西部，东至湘潭市竹埠港建筑垃圾再利用有限公司围墙，北至荒地，西至荒地，南至村道",9034.78,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.11,4303042260055,"湘潭市竹埠港老工业区地块-竹埠片区7","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西部",641.38,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.12,4303042260056,"湘潭市竹埠港老工业区地块-竹埠片区8-1","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内中部",3402.39,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.13,4303042260057,"湘潭市竹埠港老工业区地块-竹埠片区8-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内中部",299.36,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.14,4303042260058,"湘潭市竹埠港老工业区地块-竹埠片区9-1","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西部",7504.26,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.15,4303042260059,"湘潭市竹埠港老工业区地块-竹埠片区9-2","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西部",2065.73,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.16,4303042260060,"湘潭市竹埠港老工业区地块-竹埠片区9-3","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西北部",1723.58,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.17,4303042260061,"湘潭市竹埠港老工业区地块-竹埠片区10","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西部",6464.52,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.18,4303042260062,"湘潭市竹埠港老工业区地块-竹埠片区11","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西北部",133.49,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.19,4303042260063,"湘潭市竹埠港老工业区地块-竹埠片区12","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西北部",1795.59,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足绿地与开敞空间土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[{"v":6.2,"d":"6.20"},4303042260064,"湘潭市竹埠港老工业区地块-竹埠片区13","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内南部，东至荒地，南至荒地，西至湘潭市竹埠港建筑垃圾再利用有限公司围墙，北至村道",1435.95,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[6.21,4303042260065,"湘潭市竹埠港老工业区地块-竹埠片区14","湖南","湘潭市","湘潭市岳塘区荷塘街道竹埠村","竹埠港竹埠片区内西北部",1499.83,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足绿地与开敞空间土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.1,4303042260024,"湘潭市竹埠港老工业区地块-双埠片区-河东沿江风光带","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内西部",6827.61,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.2,4303042260025,"湘潭市竹埠港老工业区地块-双埠片区3","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内西部",20739.72,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足居住用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.3,4303042260026,"湘潭市竹埠港老工业区地块-双埠片区4","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内中北部，东至团竹路，南至湘潭市滴水环保再生建材有限公司厂区围挡，西至竹埠港路，北至沃土路",134601.24,"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地、陆地水域、绿地与开敞空间用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.4,4303042260027,"湘潭市竹埠港老工业区地块-双埠片区5","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内西南部",5645.05,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.5,4303042260028,"湘潭市竹埠港老工业区地块-双埠片区6","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东北部",9526.32,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.6,4303042260029,"湘潭市竹埠港老工业区地块-双埠片区7","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东北部",{"v":18367.1,"d":"18367.10"},"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足公共管理与公共服务用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.7,4303042260030,"湘潭市竹埠港老工业区地块-双埠片区8","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内北部",15195.55,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足公共管理与公共服务用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.8,4303042260031,"湘潭市竹埠港老工业区地块-双埠片区9","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内中部",24217.56,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.9,4303042260032,"湘潭市竹埠港老工业区地块-双埠片区10","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内中东部，东至荒地，南至菜地水塘，西至湘潭市滴水环保再生建材有限公司厂区围挡，北至荒地",26391.68,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、陆地水域、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[{"v":7.1,"d":"7.10"},4303042260033,"湘潭市竹埠港老工业区地块-双埠片区11","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内中部",{"v":6236.9,"d":"6236.90"},"湖南湘潭岳塘经济开发区管理委员会","正在实施修复","满足交通运输用地、公共管理与公共服务用地土壤环境质量要求","湘潭大学环境与资源学院","中铁建设集团有限公司","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.11,4303042260034,"湘潭市竹埠港老工业区地块-双埠片区12","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东南部",{"v":907.8,"d":"907.80"},"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.12,4303042260035,"湘潭市竹埠港老工业区地块-双埠片区13","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东部",51103.51,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.13,4303042260036,"湘潭市竹埠港老工业区地块-双埠片区14","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内中南部，东至竹埠港路，南至湘潭市鑫旺金属再生利用有限公司，西至荒地，北至荒地",2675.13,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.14,4303042260037,"湘潭市竹埠港老工业区地块-双埠片区15","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内南部，东至荒地，南至荒地，西至竹埠港路，北至荒地",27498.79,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足交通运输用地、商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.15,4303042260038,"湘潭市竹埠港老工业区地块-双埠片区16","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东南部",15674.55,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.16,4303042260039,"湘潭市竹埠港老工业区地块-双埠片区17","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内东南部",{"v":19020.1,"d":"19020.10"},"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.17,4303042260040,"湘潭市竹埠港老工业区地块-双埠片区18","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内南部，东至竹埠港路，南至荒地，西至村道，北至滴水埠村民居",{"v":16726.9,"d":"16726.90"},"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足居住用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[7.18,4303042260041,"湘潭市竹埠港老工业区地块-双埠片区19","湖南","湘潭市","湘潭市岳塘区荷塘街道双埠村","竹埠港双埠片区内南部",5365.15,"湖南湘潭岳塘经济开发区管理委员会","已开展风险评估","满足商业服务业用地土壤环境质量要求","未明确","未明确","湖南湘潭岳塘经济开发区管理委员会","2020.7.23"]
[8,4307032320009,"鼎城区原武陵精锑冶炼厂","湖南","常德市","常德市鼎城区灌溪镇大垱村","西侧临近渐河，南侧为林地",7356.91,"鼎城区灌溪镇溪沿社区（原大垱村）","已编制风险管控方案，并已按照相关要求开展制度管控。","相应区域分别满足交通运输用地、绿地与开敞空间用地、居住用地土壤环境质量要求","湖南润万环保科技有限公司","常德市浩丰建筑工程有限公司","常德市鼎城区灌溪镇人民政府","2020.7.17"]
[9,4302042990025,"株洲石英化玻有限责任公司地块","湖南","株洲市","株洲市石峰区清水路222号","南面紧依清水路、株洲化工厂，北面紧邻湘黔铁路，东面为株洲化工厂劳动服务公司仓库，西面为商铺门面",7173.692,"株洲市清水塘园区开发建设有限公司","已开展风险评估","满足工矿用地、绿地与开敞空间用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2021.1.26"]
[10,4306812320009,"汨罗市古培铜材厂遗留地块","湖南","岳阳市","湖南省汨罗市古培镇","西侧为石牛冲居民区、东侧为新屋里居民区、北侧及南侧均为农田",9745,"汨罗市古培镇人民政府","正在编制风险管控修复方案","满足居住用地土壤环境质量要求","湖南净源环境工程有限公司","未明确","汨罗市人民政府","2020.9.25"]
[11,4302042450042,"株洲市煤气公司地块","湖南","株洲市","株洲市石峰区建设北路126号","西侧和南侧为工业企业，北侧为株化职工宿舍，东侧居民区和新奥广场",176526.49,"株洲市石峰区土地储备中心","正在编制风险管控修复方案","满足公共管理与公共服务用地、居住用地、绿地与开敞空间用地土壤环境质量要求"," 中机国际工程设计研究院有限责任公司","未明确","未明确","2020.10.15"]
[12,4311242320017,"道县惠民矿业投资有限公司","湖南","永州市","永州市道县仙子脚镇仙子脚村西南","东侧为道县远华矿业投资有限公司，西侧为荒山，北侧为荒地及荒弃果园，南侧为道路及荒地",21403.9,"道县人民政府","已编制风险管控/修复方案","满足工矿用地土壤环境质量要求","湖南德益环保工程有限公司","道县莲城集团有限公司","永州市生态环境局道县分局","2020.10.23"]
[13,4302042770138,"清水冶化有限责任公司","湖南","株洲市","株洲市石峰区清水乡建设村袁家湾","西南侧为株冶集团厂区，地块南面、西南面、东南面周边有清霞社区",26097,"集体土地","已完成效果评估 ","满足工矿用地土壤环境质量要求"," 中机国际工程设计研究院有限责任公司","湖南恒凯环保科技投资有限公司","株洲市清水塘投资集团有限公司","2020.12.8"]
[14,4331232090012,"凤凰县蓝翔化工厂地块","湖南","湘西自治州","凤凰县沱江镇杜田村","位于凤凰县沱江镇杜田村，地理坐标为北纬27°57'12\"，东经109°37'21\"。地块北侧为县道047，南侧为山坡及农田，厂区西侧即为沱江，直线距离约200m，东侧为居民点及农田。",10600,"凤凰县人民政府","正在实施修复","满足商业服务业用地土壤环境质量要求","湖南衡宇数据咨询有限公司，协作单位：长沙水天净化技术工程有限公司","湖南省和清环境科技有限公司","凤凰县城市建设投资开发有限责任公司","2020.12.24"]
[15,4302042260060,"湖南海利化工有限公司地块","湖南","株洲市","位于清水塘工业区，铜霞路461号，西北侧为清水塘霞湾污水处理厂","地块西北侧为清水塘霞湾污水处理厂，地块西侧为原宏基锌业厂区，地块东侧分别为原新都实业厂区（已拆除）、原云龙实业厂区（已拆除）、原祥凤实业厂区（已拆除）；地块南侧为原大湖区域（现为驾校训练场地）",116245.7,"株洲市石峰区土地储备中心","已完成效果评估 ","满足商业服务业用地、绿地与开敞空间用地土壤环境质量要求"," 湖南中森环境科技有限公司"," 湖南凯迪工程科技有限公司","株洲市清水塘投资集团有限公司","2021.1.27"]
[16,4301122260002,"湖南海利化工股份有限公司","湖南","长沙市","长沙市望城区高塘岭镇高裕北路58号","地块东北至高裕北路、西至高塘岭西街、南至地块边界",74260,"土地使用证已注销，实际使用权人暂为湖南海利化工股份有限公司","正在实施风险管控/修复","满足居住用地土壤环境质量要求","湖南省环境保护科学研究院","未明确","湖南海利化工股份有限公司试验工场","2021.2.2"]
[17,4302042320180,"株冶1","湖南省","株洲市","株洲市石峰区清水塘工业区","东至清水塘大道，西至规划道路；南至铜霞路，北至规划株冶路二期。",99063.78,"株洲清水塘产业经济发展有限公司","已开展风险评估","满足工矿用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[18,4302042320182,"株冶3","湖南省","株洲市","株洲市石峰区清水塘工业区","东至规划道路，西至清霞路三期；北至规划道路",21806.94,"株洲市土地储备中心","已开展风险评估","满足工矿、供电用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[19,4302042320183,"株冶4","湖南省","株洲市","株洲市石峰区清水塘工业区","东至规划道路，西至清霞路三期；南至规划道路，北至规划株冶路二期。",46439.65,"株洲清水塘产业经济发展有限公司","已开展风险评估","满足工矿用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[20,4302042320184,"株冶5","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶1地块，西至株冶4地块；南至株冶3地块，北至规划株冶路二期。",19063.17,"株洲市土地储备中心","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[21,4302042320185,"株冶6","湖南省","株洲市","株洲市石峰区清水塘工业区","东至清水塘大道，西至清霞路三期；南至株冶1、株冶2、株冶4地块，北至株冶11、株冶13、株冶16、株冶18地块。",26108.14,"株洲市土地储备中心","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[22,4302042320188,"株冶9","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶13地块，西至株冶16地块，南至株冶13地块，北至株冶10地块",28382.86,"株洲市清水塘投资集团有限公司","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[23,4302042320189,"株冶10","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶8地块，西至株冶17地块，南至株冶9地块，北至株冶15地块",25497.2,"株洲市清水塘投资集团有限公司","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[24,4302042320190,"株冶11","湖南省","株洲市","株洲市石峰区清水塘工业区","东至原株冶污水处理厂，西至株冶13地块；南至规划株冶路二期，北至株冶8地块。",12886.72,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[25,4302042320194,"株冶15","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶14地块，西至株冶21地块；南至株冶10地块，北至原株化厂区。",31194.86,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[26,4302042320195,"株冶16","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶9地块，西至株冶18地块；南至规划株冶路二期，北至株冶17地块",34692.36,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[27,4302042320196,"株冶17","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶10地块，西至株冶20地块；南至株冶16地块，北至株冶21地块。",37700.89,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[28,4302042320197,"株冶18","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶16地块，西至株冶19地块；南至规划株冶路二期，北至株冶20地块。",22545.1,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[29,4302042320198,"株冶19","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶18地块，西至株冶办公楼，南至清霞路绿化带，北至株冶20地块",34563.58,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[30,4302042320199,"株冶20","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶17地块。西至株冶办公楼区域，南至株冶18和株冶19地块，北至株冶21地块",46219.78,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[31,4302042320200,"株冶21","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶15地块，西至株冶办公楼区域，南至株冶17和株冶20地块，北至原中盐湖南株洲化工集团有限公司",21922.83,"株洲市土地储备中心","已开展风险评估","满足综合用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[32,4302042320201,"株冶22","湖南省","株洲市","株洲市石峰区清水塘工业区","东至原中盐湖南株洲化工集团有限公司，西至清竹社区，南至株冶办公楼区域，北至株冶23地块",9075.15,"株洲市土地储备中心","已开展风险评估","满足交通运输用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[33,4302042320202,"株冶23","湖南省","株洲市","株洲市石峰区清水塘工业区","东至原中盐湖南化工集团有限公司，西至清竹社区菜地；南至株冶22地块，北至原原株洲中盛塑胶有限公司。",24725.52,"株洲市土地储备中心","已开展风险评估","满足工矿用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[34,4302042320203,"株冶26地块","湖南省","株洲市","株洲市石峰区清水塘工业区","东至清水塘大道，西至原湖南盈德气体有限公司；南至铜霞路，北至株冶1地块。",10303.49,"株洲市土地储备中心","已开展风险评估","满足防护绿地用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[35,4302042320204,"株冶27地块","湖南省","株洲市","株洲市石峰区清水塘工业区","东至株冶19地块，西至三一能源装备有限公司。",12136.1,"株洲市土地储备中心","已开展风险评估","满足防护绿地、交通运输用地土壤环境质量要求","未明确","未明确","株洲市清水塘投资集团有限公司","2024.9.29"]
[36,4306822770006,"临湘市原农药厂及周边地块","湖南","岳阳市","临湘市江南镇","东侧边界外临近陆城镇政区，西侧和北侧边界外临近长江，东南侧紧靠莼湖社区",73400,"临湘市江南镇人民政府","正在实施风险管控","满足绿地与开敞空间用地土壤环境质量要求","顶鑫环保科技有限公司","湖南亿恒环保工程有限公司","临湘市人民政府","2021.1.15","2023年9月18日，进行了效果评估，于2023年12月18日完成了效果评估备案，因未达到安全利用，暂不移出目录"]
[37,4302042260139,"石峰区株洲经仕集团实业有限公司地块","湖南","株洲市","株洲市清水塘工业区响田西路321号","东至石峰公园、南至玉桂小区、西至响田西路、北至云峰阁社区",49388.13,"株洲市石峰区土地储备中心","已开展风险评估","目前规划正在调整，暂无法确定，后续根据地块开发需要确定","未明确","未明确","未明确","2021.9.10"]
[38,4304062320003,"衡阳市德隆再生金属有限公司地块","湖南","衡阳市","衡山科学城","地块位于衡山科学城大道以北、雁鸣路以西，地块东侧为创新区，西侧和东南侧为居民聚集点",11678.37,"衡山科学城管理委员会","正在编制风险管控/修复方案","满足工矿用地用地土壤环境质量要求","湖南晶康环保科技有限公司","未明确","衡山科学城管理委员会","2021.10.9"]
[39,4304822260027,"湖南水口山有色金属集团有限公司水口山有色金属有限责任公司柏坊铜矿","湖南","衡阳市","常宁市柏坊镇大新村","东至废渣场围墙、南至冰铜厂、西至雨水收集系统围墙、北至硫酸系统围墙",100772.35,"水口山有色金属有限责任公司","已开展风险评估","满足工矿用地用地土壤环境质量要求","湖南有色金属研究院有限责任公司","未明确","水口山有色金属有限责任公司","2021.9.17"]
[40,4304823320069,"水口山有色金属有限责任公司第三冶炼厂（湖南黑铅冶炼厂）地块","湖南","衡阳市","衡阳市水口山镇常青路","北至湘江，南至水口山镇常青路，东侧居民区（已集体搬迁），西至水口山机电公司",105356.05,"水口山有色金属有限责任公司","已开展风险评估","满足公共管理与公共服务用地土壤环境质量要求","湖南有色金属研究院有限责任公司","未明确","水口山有色金属有限责任公司","2021.12.9"]
[41,4304823320068,"水口山有色金属有限责任公司第四冶炼厂地块","湖南","衡阳市","衡阳市水口山镇常青路","北至水口山镇常青路，南至农田（现已施工修复、未见种粮食），东侧五矿铍业，西至居民区",127042.73,"水口山有色金属有限责任公司","已开展风险评估","满足工矿用地用地土壤环境质量要求","湖南有色金属研究院有限责任公司","未明确","水口山有色金属有限责任公司","2021.12.9"]
[42,4305212250011,"邵东县牛马司城建洗煤铸造焦化厂（一厂区）地块","湖南","邵阳市","邵阳市邵东市牛马司镇桐杨村","地块北侧40m为320国道，南侧为原娄邵铁路，东西两侧均为桐杨村池塘及菜地。",5686,"邵东市人民政府","正在编制修复方案","满足居住用地土壤环境质量要求","湖南维景环保科技有限公司","未明确","邵东市人民政府","2022.3.14"]
[43,4304062990006,"衡阳市科思化工实业有限公司地块","湖南","衡阳市","湖南省衡阳市雁峰区白沙洲金龙村四组","东至金龙村居民点，南至金龙村居民点，西至金龙包装厂（已拆除），北至同安福龙湾小区南侧道路。",4481.32,"衡阳高新技术产业开发区管理委员会","已开展风险评估","满足一类仓储用地土壤环境质量要求","未明确","未明确","未明确","2022.4.23"]
[44,4306032260018,"岳阳市云溪区天顺化工厂地块","湖南","岳阳市","岳阳市云溪区陆城镇天螺山的陆城村边缘地带","北临长江，东面紧邻临湘市化学农药厂，西面为农田，南面为水塘。",8300,"岳阳市云溪区陆城镇人民政府","正在编制风险管控/修复方案","满足绿地土壤环境质量要求","北京中金万瑞工程咨询有限公司","未明确","岳阳晨宇环境综合治理有限公司","2022.4.28"]
[45,4311242260028,"道县化工厂","湖南","永州市","永州市道县西洲街道小江口社区","永州市道县西洲街道小江口社区原道县化工厂，中心地理坐标为经度\n\nE111°35′35″、纬度 N25°29′42″ \n",27902.75,"道县人民政府","正在编制风险管控/修复方案","满足公共服务用地土壤环境质量要求","顶鑫环保科技有限公司","长沙德邦环保技术有限公司","道县人民政府","2023.3.3"]
[46,4301212260035,"长沙县北山镇湘欧化工厂","湖南","长沙市","长沙县北山镇石常村蛇皮冲 组","西至道路分界，北至石常村居民点，东至山地，南临山林荒地",5200,"长沙县北山镇人民政府","已开展风险评估","满足公共服务机关团体用地土壤环境质量要求","未明确","未明确","未明确","2023.3.15"]
[47,4301812090010,"浏阳市原永安锌厂地块","湖南","长沙市","浏阳市永安镇丰裕社区","北面为湖南天联环保建材有限公司，东至农田，西至农田，南侧为捞刀河",46567.24,"浏阳市永安镇人民政府","已开展风险评估","满足绿地土壤环境质量要求","未明确","未明确","未明确","2023.3.15"]
[48,4305232770017,"邵阳芳鑫金属材料开发有限公司地块","湖南","邵阳市","湖南省邵阳市邵阳县黄亭市镇永塘村","地块西侧为农田，地块南侧为农田，地块永塘村、东侧为邵阳县彩鑫制釉有限公司",30668,"邵阳县人民政府","正在编制效果评估报告","满足工业用地土壤环境质量要求","湖南弘毅环保科技有限公司","湖南久正环保科技有限公司","邵阳县人民政府","2023.6.5"]
[49,4305213090012,"邵东市石株桥铅锌矿地块","湖南","邵阳市","邵阳市邵东市灵官殷镇铁塘村","东至林地范围，西至林地范围，北至耕地范围，南至水塘北侧。",6081,"邵东市人民政府","正在编制风险管控/修复方案","满足居住用地土壤环境质量要求","湖南思源环保技术有限公司","未明确","未明确","2023.6.5"]
[50,4304812310010,"耒阳市阳光金属再生资源有限公司污染场地地块","湖南","衡阳市","耒阳市余庆乡龙陂村","地块东侧为村户（龙陂村5、10组），地块东北侧为联平新城，内设有中小学和幼儿园；地块南、北和西面为山。",35398.91,"衡阳市耒阳市人民政府","已开展风险评估","满足居住用地土壤环境质量要求","未明确","未明确","未明确","2023.6.5"]
[51,4306242990020,"原湘阴县文星镇洋沙湖大道长江化肥（湖南）有限公司地块","湖南","岳阳市","湖南省岳阳市湘阴县文星镇八甲村","地块北侧为白水江和湘江，地块南侧为东山社区居民，地块东侧为水塘，地块西侧为水塘",61328.47,"湘阴县城市发展集团有限公司","已开展风险评估","满足中小学用地土壤环境质量要求","湖南方瑞节能环保咨询有限公司","未明确","湘阴县土地储备中心","2023.12.18"]
[52,4309222320159," 桃江县江南冶金有限公司遗留地块","湖南","益阳市","桃江县马迹塘镇石门村村民委员会","地块北、东和西侧均为山林，南侧是民房和541乡道",9401,"桃江县马迹塘镇人民政府","已开展风险评估","满足绿地与开敞空间用地土壤环境质量要求","湖南城市学院设计研究院有限公司","湖南新九方科技有限公司","桃江县马迹塘镇人民政府","2023.11.16"]
[53,4309222320161,"桃江县神龙锑业有限公司遗留地块","湖南","益阳市","益阳市桃江县桃花江镇","地块北至划船港村村民住宅，东、南、西至山林地",5987,"桃江县桃花江镇人民政府","已开展风险评估","满足绿地与开敞空间用地土壤环境质量要求","湖南城市学院设计研究院有限公司","湖南新九方科技有限公司","桃江县桃花江镇人民政府","2023.11.16"]
[54,4304822260067,"湖南省衡阳市康华化肥工业有限责任公司","湖南","衡阳市","湖南省常宁市松柏镇大渔村","东侧为衡阳市大宇锌业有限公司已搬迁闲置用地，南侧为荒地、西侧为大渔村、北侧为荒地",105347.9,"湖南省康华化肥工业有限责任公司","已开展风险评估","满足一类用地(居住用地)土壤环境质量要求","未明确","未明确","未明确","2024.3.4"]
[55,4302042290150,"株洲中盛塑胶有限公司地块","湖南","株洲市","湖南省株洲市石峰区清水路473号","地块南邻株冶集团，东面为株化集团",67131,"株洲市石峰区土地储备中心","已开展风险评估","满足居住用地和道路用地土壤环境质量要求","未明确","未明确","未明确","2024.3.15"]
[56,4302042260061,"柳化中成化工有限公司地块","湖南","株洲市","铜塘湾街道湘珠路216号","东至湘珠路、南至农田、北至株洲市煤气公司、西至中盐湖南株洲化工集团有限公司",57899.44,"株洲市石峰区土地储备中心","已开展风险评估","满足防护绿地、水域和道路土壤环境质量要求","未明确","未明确","未明确","2024.3.22"]
[57,4302042260160,"湖南柳化桂成化工有限公司地块二","湖南","株洲市","湖南省株洲市石峰区建设北路1493号","西至中成化工，东至规划路，南至规划路，北至规划路",366965.84,"株洲市石峰区土地储备中心","正在编制风险管控修复方案","满足工业用地、公园绿地、商业用地、防护绿地以及道路土壤环境质量要求","中机国际工程设计研究院有限责任公司","未明确","未明确","2024.3.22"]
[58,4302042260161,"湖南柳化桂成化工有限公司地块三","湖南","株洲市","湖南省株洲市石峰区建设北路1493号","北至规划路，南至中南管件厂，西至清水塘大道，东至株洲农资仓库",26495.8,"株洲市石峰区土地储备中心","正在编制风险管控修复方案","满足物流仓储用地及道路土壤环境质量要求","中机国际工程设计研究院有限责任公司","未明确","未明确","2024.3.22"]
[59,4303812190018,"湘潭市12家重点行业关停企业(一期)— 湘乡市龙洞镇韶龙制革厂地块","湖南","湘潭市","湖南省湘潭市湘乡市龙洞镇七星村（合并为楠香村）","西北侧以G240国道及厂区围墙为界，东北、东南及西南侧以厂区围墙为界",3258.96,"湘乡市龙洞镇人民政府","已开展风险评估","满足居住用地土壤环境质量要求","深圳粤鹏环保技术股份有限公司","未明确","湘乡市龙洞镇人民政府","2024.6.28"]
[60,4303812190016,"湘潭市12家重点行业关停企业(一期)— 湖南红东方制革有限公司地块","湖南","湘潭市","湖南省湘潭市湘乡市望春门街道桑枣村","西北侧以梅桑东路为界，东南侧毗邻涟水，西侧以湘乡亿润彩色印刷有限公司厂房界",8822.32,"湘乡市望春门街道","已开展风险评估","满足居住用地土壤环境质量要求","深圳粤鹏环保技术股份有限公司","未明确","湘乡市望春门街道","2024.6.28"]
[61,4302042260030,"湖南京西祥隆化工有限公司地块","湖南","株洲市","株洲市石峰区湘珠路131号","北邻湘黔铁路，清水路以南，清响路以北",27408.43,"株洲市清水塘投资集团有限公司","正在编制风险管控修复方案","满足二类建设用地土壤环境质量要求","湖南地质实验测试中心","未明确","株洲市清水塘投资集团有限公司","2024.8.28","2019.7.15，按一类用地已开展风险评估，因用地规划调为二类用地，本次重新评审。"]
[62,4302042260031,"株洲邦化化工有限公司地块","湖南","株洲市","株洲市石峰区湘珠路131号","北侧紧邻湘株路，东侧为柳化集团湖南智成化工有限公司原厂址，南侧为福尔程化工有限公司原厂址，西侧为京西祥隆化工有限公司原厂址",21374.4,"株洲市清水塘投资集团有限公司","正在编制风险管控修复方案","满足二类建设用地土壤环境质量要求","湖南地质实验测试中心","未明确","株洲市清水塘投资集团有限公司","2024.8.28","2019.7.15，按一类用地已开展风险评估，因用地规划调为二类用地，本次重新评审。"]
[63,4302042260032,"株洲福尔程化工有限公司地块","湖南","株洲市","株洲市石峰区湘珠路131号","东面和南面区域为智成化工有限公司原厂址、西至湖南中成化工有限公司原厂址，北至湖南京西祥隆化工原厂址",30492,"株洲市清水塘投资集团有限公司","正在编制风险管控修复方案","满足二类建设用地土壤环境质量要求","湖南地质实验测试中心","未明确","株洲市清水塘投资集团有限公司","2024.8.28","2019.7.15，按一类用地已开展风险评估，因用地规划调为二类用地，本次重新评审。"]
[64,4303212260056,"湘潭县易俗河镇红燕山片区（一期）地块","湖南","湘潭市","湘潭县易俗河镇樟树村、杨溪村","北至滴水止，东至围墙止，南至围墙止，西至围墙止",17916.6,"湖南湘潭天易经开区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","湖南湘潭天易经开区管理委员会","2024.9.25"]
[65,4302042260062,"湖南昊华化工有限公司地块","湖南","株洲市","株洲市石峰区丁山路69号","北至中南管件有限责任公司，南至亿达实业有限公司，东至天元农资有限公司，西至亚合置业有限公司",64706.2,"株洲市清水塘投资集团有限公司","正在编制风险管控修复方案","满足二类建设用地土壤环境质量要求","中机国际工程设计研究院有限责任公司","未明确","株洲市清水塘投资集团有限公司","2024.9.5"]
[66,4331242080029,"花垣县西部锰业制品有限责任公司地块","湖南","湘西自治州","花垣县花垣镇花桥村","西至国道209，东至围墙止，南至围墙止，北至围墙止",20419.9,"花垣县人民政府","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省勘测设计院有限公司","中铁城建集团第二工程有限公司","花垣县十八洞紫霞湖美综合开发有限公司","2024.12.17"]
[67,4331242080014,"花垣县峰云矿业有限责任公司地块","湖南","湘西自治州","花垣县花垣镇狮子桥村","南至冲沟顶部，北至围墙止，西至围墙止，东至围墙止",32008.04,"花垣县人民政府","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省勘测设计院有限公司","中铁城建集团第二工程有限公司","花垣县十八洞紫霞湖美综合开发有限公司","2024.12.17"]
[68,4331242080024,"花垣县文华锰业有限责任公司地块","湖南","湘西自治州","湖南省湘西土家族苗族自治州花垣县花垣镇狮子桥村","南至围墙，北至围墙，西至国道209，东至山顶部",{"v":25537.16,"d":"25537"},"花垣县人民政府","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省勘测设计院有限公司","中铁城建集团第二工程有限公司","花垣县十八洞紫霞湖美综合开发有限公司","2025.4.29"]
[69,4301042990390,"滨江新城遗留工业场地原湘岳化工厂地块","湖南","长沙市","湖南湘江新区观沙岭街道滨江新城原三汊矶老工业区","地块东侧邻近滨江景观大道，临近湘江西岸，南侧为原长沙铬盐厂，西侧和北侧为岳华村（已动迁）和津城巷",44432,"湖南湘江新区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省环境保护科学研究院、湖南中森环境科技有限公司","未明确","长沙市铬污染物治理有限公司","2025.05.21"]
[70,4301042990399,"滨江新城遗留工业场地原长沙锌厂一号地块","湖南","长沙市","湖南湘江新区观沙岭街道滨江新城原三汊矶老工业区","地块东侧临近湘江西岸，西侧和北侧为滨江景观大道，南侧为原银盆北路，邻近三汊矶码头",6922,"湖南湘江新区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省环境保护科学研究院、湖南中森环境科技有限公司","未明确","长沙市铬污染物治理有限公司","2025.05.21"]
[71,4301042990391,"滨江新城遗留工业场地原长沙锌厂二号地块","湖南","长沙市","湖南湘江新区观沙岭街道滨江新城原三汊矶老工业区","地块东侧临近湘江西岸（不含滨江景观大道），西侧为规划潇湘北路，邻近银谷北津城，南侧为北津城路，北侧为原长沙铬盐厂",42272,"湖南湘江新区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省环境保护科学研究院、湖南中森环境科技有限公司","未明确","长沙市铬污染物治理有限公司","2025.05.21"]
[72,4301042990392,"滨江新城遗留工业场地原长沙锌厂三号地块","湖南","长沙市","湖南湘江新区观沙岭街道滨江新城原三汊矶老工业区","地块东侧临近湘江西岸（不含滨江景观大道），西侧为规划潇湘北路，邻近银谷北津城，南侧为北津城路，北侧为原长沙铬盐厂。",59232,"湖南湘江新区管理委员会","已开展风险评估","满足一类建设用地土壤环境质量要求","湖南省环境保护科学研究院、湖南中森环境科技有限公司","未明确","长沙市铬污染物治理有限公司","2025.05.21"]
[73,4303812260040,"湘潭市 12 家重点行业关停企业（一期）—湘乡诺立新科材料有限公司地块","湖南","湘潭市","湘乡市昆仑桥街道","北侧以山林界，东侧以韶山灌区北干渠为界，南侧以山林界，西侧以山林界",19987.73,"湘潭市生态环境局湘乡分局","已开展风险评估","满足一类建设用地土壤环境质量要求","深圳粤鹏环保技术股份有限公司","未明确","湘潭市生态环境局湘乡分局","2025.6.10"]
[74,4303812260039,"湘潭市 12 家重点行业关停企业（一期）—湖南鑫丽锑业科技有限公司地块","湖南","湘潭市","湘乡市新湘路办事处","北侧以围墙为界，东侧以村道界，南侧以围墙界，西侧以围墙界",5251.11,"湘乡市科技和工业信息化局","已开展风险评估","满足二类建设用地土壤环境质量要求","深圳粤鹏环保技术股份有限公司","未明确","湘乡市科技和工业信息化局","2025.6.10"]
[75,4312242320026,"溆浦县东新矿业有限公司地块","湖南","怀化市","溆浦县东新矿业有限公司地块位于溆浦县低庄镇阳兴村三组","地块中心坐标\n为：东经 110.70748°，北纬 28.05511°",23283.36,"溆浦县工业和信息化局","已开展风险评估","满足二类建设用地土壤环境质量要求","长沙宸甄环保科技有限公司","未明确","溆浦县工业和信息化局","2025.6.13"]
[76,4303023250042,"湘潭合力焦化地块风险评估报告","湖南","湘潭市","湘潭市雨湖区鹤岭镇","地块北侧紧邻鹤岭污水处理厂外，其它方向相邻的位置为村庄、菜地、农田、山地等",98520.24,"湘潭高建创科商贸有限公司","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","湘潭高建创科商贸有限公司","2025.9.8"]
[77,4304812320026,"耒阳市永鑫有色金属综合再生有限公司地块环境风险评估报告","湖南","衡阳市","湖南省衡阳市耒阳市灶市街联平村七组","地块北侧为居民区（联平新城），居民区内设有中小学和幼儿园；地块东、南和西面为农田。",50835,"耒阳市城市和农村建设投资集团有限公司","已开展风险评估","满足二类用地土壤环境质量要求","未明确","未明确","未明确","2025.9.19"]
[78,4331242310265,"原花垣县浩宇化工有限责任公司地块土壤污染风险评估报告","湖南","湘西自治州","花垣县花垣镇下瓦水村","东至现状林地，南至原残联选厂尾矿库，西至原残联选厂，北至花垣县浩宇化工有限责任公司锰渣库",33887,"花垣县国晟资产经营有限公司","已开展风险评估","满足二类建设用地土壤环境质量要求","国检测试控股集团（湖南）华中科技有限公司","国检测试控股集团（湖南）华中科技有限公司","花垣县国晟资产经营有限公司","2025.9.25"]
[79,4331244310192,"原花垣县金诚锰业有限责任公司地块土壤污染风险评估报告","湖南","湘西自治州","湘西土家族苗族自治州花垣县花垣镇王二桥村","东面为居民住宅及村道，南面为居民点及乡村道路，西测为农田，北面为居民点及农田",16557.68,"花垣县国晟资产经营有限公司","已开展风险评估","满足二类建设用地土壤环境质量要求","国检测试控股集团（湖南）华中科技有限公司","国检测试控股集团（湖南）华中科技有限公司","花垣县国晟资产经营有限公司","2025.9.25"]
[80,4331242080030,"原花垣县吉达锰业有限责任公司地块土壤污染风险评估报告","湖南","湘西自治州","花垣县花垣镇洞溪坪村","东面为山体，南面 80m 处为农田，西面距 209 国道约 600m，地块北面为其锰渣库（旧）和山林。",19676.51,"花垣县国晟资产经营有限公司","已开展风险评估","满足二类建设用地土壤环境质量要求","国检测试控股集团（湖南）华中科技有限公司","国检测试控股集团（湖南）华中科技有限公司","花垣县国晟资产经营有限公司","2025.9.26"]
[81,4306022290023,"原际华三五一七橡胶制品有限公司一号地块风险评估报告","湖南","岳阳市","岳阳市岳阳楼区岳阳楼街道洞庭北路71号","紧邻汴河园路，西、北临洞庭湖，最近处距洞庭湖约 0.4km",108238.72,"岳阳市岳阳楼区汇城发展集团有限公司","已开展风险评估","满足建设用地第一类用地土壤环境质量要求","湖南唯众环保科技有限公司","未明确","岳阳市岳阳楼区汇城发展集团有限公司","2025.9.29"]
[82,4306022260076,"原际华三五一七橡胶制品有限公司二号地块风险评估报告","湖南","岳阳市","岳阳市岳阳楼区岳阳楼街道洞庭北路71号","北至洞庭书香苑，南至际华路，西至岳阳敏敏儿耳公寓，东至汴河园路",61829.58,"岳阳市岳阳楼区汇城发展集团有限公司","已开展风险评估","满足建设用地第一类用地土壤环境质量要求","湖南唯众环保科技有限公司","未明确","岳阳市岳阳楼区汇城发展集团有限公司","2025.9.29"]
[83,4306022260047,"东风湖新区己内酰胺片区周边区域 1 号地块","湖南","岳阳市","岳阳市岳阳楼区","沿湖路以东，杭瑞高速以南，东风湖以北",168406.51,"岳阳市自然资源和规划事务中心","已开展风险评估","满足二类建设用地土壤环境质量要求","湖南省环境保护科学研究院、中国环境科学研究院、湖南省勘测设计院有限公司","未明确","岳阳市自然资源和规划事务中心","2025.10.17"]
[84,4306022260049,"东风湖新区己内酰胺片区周边区域7 号地块","湖南","岳阳市","岳阳市岳阳楼区","已内酰胺事业部东南侧",101782.21,"岳阳市自然资源和规划事务中心","已开展风险评估","满足一类建设用地土壤环境质量要求","生态环境部土壤与农业农村生态环境监管技术中心、中国环境科学研究院、湖南省环境保护科学研究院、湖南省勘测设计院有限公司","未明确","岳阳市自然资源和规划事务中心","2025.10.17"]
[85,4302112320005,"株洲市天元区雷打石冶炼厂地块","湖南","株洲市","株洲市天元区雷打石镇公道街116号","地块东侧为石灰厂，南侧为雷打石镇居住区，西侧为空地，北侧为水塘",5700,"株洲市天元区雷打石镇人民政府","已开展风险评估","满足一类建设用地土壤环境质量要求","未明确","未明确","株洲市天元区雷打石镇人民政府","2025.10.22"]
[86,4302112320004,"湖南经仕集团铅业有限公司地块","湖南","株洲市","株洲市天元区群丰镇新文村","南侧为中南有色金属有限公司，北侧紧邻株洲市亿丰新材料有限公司，东西两侧均为未利用地",20636.4,"株洲市天元区群丰镇人民政府","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","株洲市天元区群丰镇人民政府","2025.10.23"]
[87,4302214260050,"株洲兴宇化工有限公司地块","湖南","株洲市","株洲市渌口区南洲镇将军村","地块西侧为湘江，东侧为京广线，南北侧为居民区",3321.26,"株洲市渌口区南洲镇人民政府","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","株洲市渌口区南洲镇人民政府","2025.10.24"]
[88,4302042410210,"株洲中海化工地块","湖南","株洲市","株洲市石峰区白马垅路1号","西侧为时代大道与玉虹管业，其他方向为散住居民或林地",6258.6,"株洲市石峰区清水塘办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","株洲市石峰区清水塘街道办事处","2025.10.31"]
[89,4306022260077,"原际华三五一七橡胶制品有限公司三号地块风险评估报告","湖南","岳阳市","岳阳市岳阳楼区岳阳楼街道洞庭北路71号","为北至五号地块，南至驿马巷，西至鲁肃墓，东至汴河园路",29625.75,"岳阳市岳阳楼区汇城发展集团有限公司","已开展风险评估","满足建设用地第二类用地土壤环境质量要求","湖南唯众环保科技有限公司","未明确","岳阳市岳阳楼区汇城发展集团有限公司","2025.11.28"]
[90,"4304812320027","耒阳市诚松有色金属再生有限公司地块","湖南","衡阳市","湖南省衡阳市耒阳市余庆乡龙陂村13组","北侧为耒阳市中达铁合金有限公司；东北侧约700米为居民区：南侧为原耒阳市阳光金属再生资源有限公司：西面为山林。",18336,"耒阳市人民政府","已开展风险评估","满足二类用地土壤环境质量要求","未明确","未明确","未明确","2025.12.9"]
[91,4310234320070,"永兴县林峰贵金属有限责任公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧为鸿福、银鑫有限责任公司，北侧为便江，西侧与南侧为山林",6141,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[92,4310234320086,"永兴县银鑫铅业有限责任公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块北侧为鸿福贵金属有限责任公司，东侧为富康贵金属有限责任公司，西侧为林峰贵金属有限责任公司，南侧为山林",5510,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[93,4310234320034,"永兴县鸿福贵金属有限公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧为富康贵金属有限责任公司，南侧为银鑫铅业有限责任公司，西侧为林峰贵金属有限责任公司，北侧为便江",5160,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[94,4310234320052,"永兴县富康贵金属有限责任公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧为金鑫金属有限责任公司，西侧为鸿福、银鑫有限责任公司，北侧为便江，南侧为山林",18381,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[95,431023432006,"永兴县金鑫金属有限责任公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧为顺元冶炼有限公司，南侧为山林，西侧为富康贵金属有限责任公司，北侧为便江",9236,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[96,4310232320112,"永兴县顺元冶炼有限公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧为志远金属硅业有限责任公司，南侧为山林，西侧为金鑫金属有限责任公司，北侧为便江",6382,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[97,4310232320111,"永兴县志远金属硅业有限责任公司","湖南","郴州市","郴州市永兴县便江街道西河村","地块东侧、南侧为山林，北侧为便江，西侧为顺元冶炼有限公司",1983,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[98,4310234320084,"永兴县西河铅业有限公司","湖南","郴州市","郴州市永兴县便江街道塘门口村","地块东侧为意水铅业有限责任公司，南侧为便江，北侧、西侧为农田",55312.5,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[99,4310234320044,"永兴县意水铅业有限公司","湖南","郴州市","郴州市永兴县便江街道门口村","地块北侧为球冠工贸有限责任公司，西侧为西河铅业有限责任公司，东侧为马仰铅锡有限责任公司，南侧为便江",17517,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[100,4310234320038,"永兴县马仰铅锡有限责任公司","湖南","郴州市","郴州市永兴县便江街道门口村","地块东侧为村间道路，北侧为球冠工贸有限责任公司，西侧为意水铅业有限责任公司，南侧为便江",26673,"永兴县便江街道办事处","已开展风险评估","满足二类建设用地土壤环境质量要求","未明确","未明确","永兴县便江街道办事处","2025.12.11"]
[101,4310234320126,"永兴县金辉冶炼厂","湖南","郴州市","永兴县柏林镇青路村","地块东侧为华兴铅业有限责任公司，北侧为隆泰银业有限责任公司，西侧为鸿福铅业有限责任公司，南侧为中鑫老厂区",4345,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.17"]
[102,4310232320113,"永兴金山银业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为鸿福铅业有限责任公司、中鑫老厂区，北、西、南侧为荒地",12308,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.17"]
[103,4310232320114,"永兴鸿丰铅业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为金辉冶炼厂，北侧为长丰银业有限责任公司，西侧为荒地，南侧为金山银业有限责任公司",4032,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.17"]
[104,4310234320058,"永兴华泰银业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为鑫裕环保有限责任公司，北侧为庚仁银业有限责任公司，西侧为荒地，南侧为长丰银业有限责任公司",3919,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.17"]
[105,4310232320116,"永兴隆泰银业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为华宸有色金属再生利用有限责任公司，北侧为鑫裕环保有限责任公司，西侧为鸿福铅业有限责任公司，南侧为金辉冶炼厂",3452,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.17"]
[106,4310232320117,"永兴县汇丰银业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为居民区，北侧为金源、佳之佳有限责任公司，西侧为东宸有色金属再利用有限责任公司，南侧为强胜银业、华宸有色金属冶炼有限责任公司",5471,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[107,4310232320118,"永兴华辰有色金属再生利用有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为乡间道路，北侧为汇丰银业有限责任公司，西侧为强胜银业有限责任公司，南侧为兴达铅业、金丰铅业有限责任公司",2701,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[108,4310234320048,"永兴县东宸有色金属再生利用有限公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为汇丰银业、强胜银业有限责任公司，北侧为鑫裕环保有限责任公司，西侧为隆泰银业有限责任公司，南侧为华兴铅业有限责任公司",4401,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[109,4310232320119,"永兴县强胜银业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为华宸有色金属冶炼有限责任公司，北侧为汇丰银业有限责任公司，西侧为东宸有色金属再生利用有限责任公司，南侧为雄进贵金属、丰泽贵金属有限责任公司",3270,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[110,4310234320046,"永兴佳之佳有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为金源有限责任公司，北侧为荒地，西侧为鑫裕环保有限责任公司，南侧为汇丰银业有限责任公司",9425,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[111,4310232320120,"永兴金源有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为农田，北侧为荒地，西侧为佳之佳有限责任公司，南侧为汇丰银业有限责任公司",7363,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[112,4310232320121,"永兴华兴铅业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为雄进贵金属有限责任公司，北侧为东宸有色金属再生利用有限责任公司，西侧为金辉冶炼厂，南侧为荒地",3978,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[113,4310232320122,"永兴雄进贵金属有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为丰泽贵金属有限责任公司，北侧为强胜银业有限责任公司，西侧为华兴铅业有限责任公司，南侧为荒地",4396,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.18"]
[114,4310232320123,"永兴丰泽贵金属有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为兴达有限责任公司，北侧为华宸有色金属冶炼、强胜银业有限责任公司，西侧为雄进贵金属有限责任公司，南侧为荒地",2304,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.19"]
[115,4310232320124,"永兴兴达铅业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为金丰铅业有限责任公司，北侧为华宸有色金属冶炼有限责任公司，西侧为丰泽贵金属冶炼有限责任公司，南侧为荒地",2349,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.19"]
[116,4310232320125,"永兴金丰铅业有限责任公司","湖南","郴州市","永兴县柏林镇青路村","地块东侧为乡间道路，北侧为华宸有色金属冶炼有限责任公司，西侧为兴达铅业",4265,"湖南永兴经济开发区管理委员会","已开展风险评估","满足二类建设用地土壤环境质量要求","中国电建集团中南勘测设计研究院有限公司","未明确","湖南永兴经济开发区管理委员会","2025.12.19"]
[" 有关备注：1.列入建设用地土壤污染风险管控和修复名录的地块，不得作为住宅、公共管理与公共服务用地。\n          2.未达到土壤污染风险评估报告确定的风险管控、修复目标的建设用地地块，禁止开工建设任何与风险管控、修复无关的项目。\n          3.环保举报电话：12345。\n        "]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}